## Agenda
Journal de bord
DATE | HEURE | ÉVÉNEMENT
2023-03-27 | 10:00 | Création de l'équipe. Premier scrum. Choix du logiciel de gestion de projet, création du dépot GIT
2023-03-29 | 11:19 | Meeting sur la gestion de GIT, les branches. Création du site JIRA et invitation des membres. Invitation des membes sur le projet JIRA.
03-Avr | 9:00 | 2H. Visualisation des demandes, presentation des technologies disponibles et discussion du future planning.
06-Avr | 13:00 | Creation de la base de donnée et des diagrammes de classes, discussion des technologies
07-Avr | 9:00 | Ajout de tailwind et choix du thème CSS
10-Avr | 9:00 | Finition du backlog, repartition des taches pour le sprint courrant, poker-scrum
13-Avr | 11:00 | Rencontre scrum, merge partie bruno/franck et joey/nico
13-Avr | 16:00 | Added cookies, user state and object sessionHandler, added .net Jwt and react Jwt, added login interaction and user DTO
14-Avr | 8:30 | Merge tom/etienne work, created production branch, scum meeting
17-Avr | 9:00 | Presentation du projet, merge le travail des binomes
21-Avr | 12:00 | 7h de travail sur la carte profil et la validation des inputs. Scrum meeting, merging change
24-Avr | 9:00 | Scrum meeting, merging change, 8h resolution de conflit JWT token creation de la classe utile
26-Avr | 9:00 | Added input to some field with Tom
27-Avr | 9:00 | Scrum meeting, merging change, connected some front to back
28-Avr | 9:00 | Scrum meeting, merging change